## Sheet1
Broadway Projects
Date | Task | Owner | Project Deliverable | Resource | Project Status
2015-09-17 | 9 LPs | Shahid & Micah | Complete development & testing of 9 LPs |  | 50%
2015-09-17 | 2 LPs | Gareth | Complete development & testing of 2 LPs[ Tom Story & Recruit] |  | 100%
2015-09-18 | Event Search Errors | Shahid |  |  | Pending
2015-09-22 | FB-Sign up | Shahid |  | Harold -Atul | 50%
2015-09-22 | Pop-up | Matt/Shahid |  | Atul | Working
2015-09-23 | E-book FB | Shahid |  | Rachel